## Backlog
ID | Lot | Task | Scope and detail | Reference | Depends on | Complexity | Risk | Watch point | Acceptance criteria | Status
L0-01 | 0 · Project foundation | Monorepo and tooling | pnpm workspaces: apps/server, apps/client, packages/shared. Shared strict tsconfig, linter, test runner, client build tool. Node version pinned. | Spec §3 | — | M | Low | The spec doesn't mandate any specific tool. If you don't choose, the agent chooses for you. | tsc and linter pass on all 3 packages, one trivial test passes | To do
L0-02 | 0 · Project foundation | Shared types | GameState, Player, Card, Kit, PendingEffect, PersistentEffect, TurnLedger, ConnectionState in packages/shared. One single definition, imported by both server and client. | Spec §4.1 | L0-01 | M | Medium | Any duplicated domain type between client and server is immediate debt. | No domain type defined twice anywhere in the repo | To do
L0-03 | 0 · Project foundation | Effect handler registry | One typed handler per card, registered in a registry, sharing common primitives. No generic effect engine. | Spec §4.1 | L0-02 | L | High | Architecture decision not yet made. Without a ruling, the agent will produce a half-DSL that collapses on Cloning and Absorber. | Adding a card modifies no existing file outside the registry | To do
L0-04 | 0 · Project foundation | Life-loss primitives | applyDamage: shield first, excess to lives, decrements active card counters. applyLifeLoss: neither shield nor counters. Two separate functions. | Spec §4.2 · rules spec §1 | L0-02 | M | High | The single most silent error in the project. Neither the compiler nor the linter will catch it. | A shield absorbs a hit and ignores a tax; only damage decrements counters | To do
L0-05 | 0 · Project foundation | Seeded randomness | Seeded pseudo-random generator, injected everywhere a draw happens: card distribution, Sentence, special card purchase, Mirror's default target. | Spec §8 | L0-02 | S | Medium | Without a seed, no distribution or Sentence test is reproducible. | Two games launched with the same seed produce an identical distribution | To do
L0-06 | 0 · Project foundation | Colyseus server and client connection | Empty server-side room, React client connecting to it and displaying the received state. | Spec §3 | L0-01 | M | Low | — | Two tabs connected to the same room see the same state | To do
L1-01 | 1 · Vertical slice | Home screen and game creation | createRoom generates a game code, joinRoom joins by code, nickname entry. | Spec §5.2 · §7 | L0-06 | M | Low | — | One player creates, a second joins by code, both see each other | To do
L1-02 | 1 · Vertical slice | Lobby and launch | List of connected players. Host launches from 2 players onward. Rejected beyond 4. | Spec §5.2 · §7 | L1-01 | S | Low | — | Launch rejected at 1 player, entry rejected for a 5th | To do
L1-03 | 1 · Vertical slice | Initial state and turn order | GameState creation, stable turn order, starting resources as placeholder values (kits arrive in lot 4). | Spec §4.1 | L1-02, L0-05 | M | Low | Do not anticipate kits here. Hardcoded values assumed, replaced in lot 4. | A 2-player game starts with a stable turn order | To do
L1-04 | 1 · Vertical slice | Turn loop | One action per turn, pass to the next player, increment turnSequence. | Spec §4.3 · rules spec §6 | L1-03 | M | Medium | turnSequence serves as queuedAt for the effects queue: a global counter, never per player. | A second action in the same turn is rejected | To do
L1-05 | 1 · Vertical slice | Draw action | The player gains a number of points equal to their kit's Draw value. No card gained. | Rules spec §6 | L1-04 | S | Low | — | The player gains the right number of points, their turn ends | To do
L1-06 | 1 · Vertical slice | Turn timer | 30 seconds. Deadline computed and sent by the server. Automatic draw on expiry. | Spec §5.5 | L1-05 | M | Medium | The deadline comes from the server. A client-only counter is bypassable and drifts. | A turn with no action triggers a draw at 30s | To do
L1-07 | 1 · Vertical slice | Delayed resolution queue | pendingEffects per player. Resolution after the target has played their action, in ascending queuedAt order. | Spec §4.3 · rules spec §6 | L1-04 | L | High | The core of the game. An effect resolving before its target's action invalidates the entire bluffing mechanic. | An effect queued on turn 1 only resolves on its target's turn, after their action | To do
L1-08 | 1 · Vertical slice | Basic attack only | A single card implemented: play, target, queue, resolve via applyDamage. | Rules spec §2 | L1-07, L0-04 | M | Low | Do not add the other two attacks here. They arrive in lot 2. | The target loses 1 life at the right moment, never before their turn | To do
L1-09 | 1 · Vertical slice | Per-recipient view | The server builds one state per player. Private: kit, hand, exact resource values. Public: actions played, effects queue, lives, shield, card count. | Spec §5.1 · rules spec §6 | L1-03 | L | High | Do this now, not later. Filtering added after the fact leaks any field added afterward. | The payload received by a client never contains an opponent's hand | To do
L1-10 | 1 · Vertical slice | actionPlayed and actionResolved | Two distinct events: the first broadcast as soon as the action is played, the second on its resolution. | Spec §5.3 | L1-07, L1-09 | M | Medium | Conflating them breaks the public-actions visibility model. | Both events arrive separately and in the right order | To do
L1-11 | 1 · Vertical slice | Server-side validation | Full revalidation of every action: card ownership, sufficient resources, whose turn it is, valid target. | Spec §5.4 | L1-08 | M | Medium | A greyed-out client button is not validation. | An action forged from the browser console is rejected | To do
L1-12 | 1 · Vertical slice | Minimal game table | Opponents, private zone, action log, pending effects queue, timer, draw and attack actions. | Spec §7 | L1-10 | L | Medium | The action log is the screen's main organ, not a secondary panel. | A 2-player game is fully playable from the interface | To do
L1-13 | 1 · Vertical slice | Elimination and victory | Elimination at 0 lives, last survivor wins, summary end screen. | Rules spec §6 · §7 | L1-12 | M | Low | Elimination rewards are out of scope here: lot 6. | A 2-player game ends and displays the winner | To do
L2-01 | 2 · Economy and attacks | Buying and selling cards | Purchase at double the usage cost from an infinite stock. Sale at usage cost. The sold card joins the pool. | Rules spec §1 | L1-13 | M | Low | — | Points change correctly, the card enters or leaves the hand | To do
L2-02 | 2 · Economy and attacks | Upgrade points | Purchase at 10 points, resale at 7 points. | Rules spec §1 | L2-01 | S | Low | Cost modifiable by a kit ability (Upgrader, out of V1): do not hardcode 10 into the logic. | Purchase and resale correct | To do
L2-03 | 2 · Economy and attacks | Card upgrade | 1 upgrade point, permanent for the game, applied to one specific copy. | Rules spec §1 | L2-02 | M | Medium | The upgrade applies to one copy, unless a permanent kit trait overrides it (lot 4). | Only one copy upgraded, other copies unchanged | To do
L2-04 | 2 · Economy and attacks | The three attack cards | Basic attack, Strong attack, Super attack, base and upgraded versions. | Rules spec §2 | L2-03 | M | Low | Check all six values one by one against the spec's table: a damage error triggers no alert. | All 6 combinations tested, values conforming to the spec | To do
L2-05 | 2 · Economy and attacks | Mutual attacks | Equal damage: both attacks cancel out, on the retaliating player's turn. Different damage: no interaction, each resolves on its own normal turn. | Spec §4.6 | L2-04 | L | High | Rules spec §6 line 243 and note §2 line 55 still contradict this rule as of this upload. Fix the spec BEFORE implementing. | Both cases tested, plus a 3-player case with no reciprocity | To do
L2-06 | 2 · Economy and attacks | Shared pool | Fed by sales, used special cards, and eliminated players' cards. Write-only in V1. | Rules spec §1 · Spec §6.3 | L2-01 | S | Low | No V1 card reads from the pool. Do not invent a use for it. | The pool fills correctly, nothing consumes it | To do
L3-01 | 3 · Action cards | Tax | 1-life cost via applyLifeLoss. Gain 4 points, 6 in the upgraded version. The life cost always applies. | Rules spec §3 | L2-04 | S | Medium | Never applyDamage. A 1-life player can kill themself: elimination without reward (lot 6). | The shield does not intervene, no counter decrements | To do
L3-02 | 3 · Action cards | Regeneration | Up to 4 lives per use, 3 points per life, 2 points in the upgraded version. 25-life cap. | Rules spec §3 · §7 | L2-04 | S | Low | The 25-life cap applies here like on every other source of gain. | Gain capped, excess lost | To do
L3-03 | 3 · Action cards | Shield | 4 shield points, 7 in the upgraded version. Only one active shield at a time. The upgraded version blocks Thief and Spy at no shield-point cost. | Rules spec §3 | L3-02 | M | Medium | Partially overlaps with Untouchable's immunity (lot 4): redundant but no conflict. | Recreation rejected while a shield is active | To do
L3-04 | 3 · Action cards | Thief | Steals 10 points, capped at the target's amount. Upgraded version: the target loses the same amount, the user gains double. | Rules spec §3 | L3-03 | M | Medium | The theft must be flagged as such in the TurnLedger: it's excluded from upgraded Absorber's capture. | A target with 3 points loses 3, not 10 | To do
L3-05 | 3 · Action cards | Spy and visibility matrix | See the target's kit and cards until the end of the game. Upgraded version: also see all their resources. A who-sees-what-of-whom matrix in a dedicated module. | Rules spec §3 · Spec §5.1 | L1-09 | L | High | Persistent, asymmetric right, checked on every view construction. A global boolean is not enough. | The spied-on player stays invisible to others, the spy sees everything | To do
L3-06 | 3 · Action cards | Counter rule | Spy, Thief, and Mirror only. The countering card must target the source of the pending effect. Both effects cancel, both costs are paid. | Rules spec §1 · Spec §4.7 | L3-05 | M | Medium | Never applies to attack cards: those fall under L2-05. | Same card played on a third party: no cancellation | To do
L3-07 | 3 · Action cards | Turn ledger | Per player, for their most recent complete turn: lives lost from all causes, points and upgrade points actively spent, resources lost to theft. | Spec §4.4 | L3-04 | L | High | A state diff is not enough: it must distinguish what was spent from what was stolen. | The ledger correctly distinguishes active spending from third-party theft | To do
L3-08 | 3 · Action cards | Absorber | Gains the lives lost by the target during their last complete turn, resolution included. Upgraded version: also captures active spending. | Rules spec §3 | L3-07 | M | Medium | Does not allow absorbing one's own lost lives. Gain subject to the 25-life cap. | Correct absorption after a turn where the target suffered an attack and paid a tax | To do
L3-09 | 3 · Action cards | Mirror | Redirects a non-upgraded attack pending against the user. Choice among several. Unlimited redirection chain. Upgraded version: also redirects upgraded attacks and doubles the redirected attack's damage. | Rules spec §3 | L3-06 | L | High | 20s sub-choice, default = first attack in the queue toward a randomly drawn opponent. Invalid action if nothing pending. A redirection can create a mutual-attack pair. | 3-player chain tested, invalid case rejected, default applied on expiry | To do
L4-01 | 4 · Kits | Kit model and traits | Traits: alwaysUpgraded, immuneTo, allowsMultipleAttacksPerTurn. Checked on every card acquisition. | Spec §4.5 · rules spec §4 | L2-03 | M | High | alwaysUpgraded is not a flag set at distribution: it applies to any later acquisition and to every held copy. | The trait applies to a card acquired after the start of the game | To do
L4-02 | 4 · Kits | Starting distribution | Kit resources, random draw of action and attack cards per the roster's quantities, duplicates possible, kit's special cards. | Rules spec §4 · §6 | L4-01, L0-05 | M | Medium | Replaces the placeholder values from lot 1 (L1-03). | Quantities conforming to the roster for the 4 kits in the lot | To do
L4-03 | 4 · Kits | Kamikaze and Untouchable | Starting stats for both kits. Untouchable: immunity to Thief and Spy. | Rules spec §4 | L4-02 | M | Medium | Should the immunity block Spy Thief? Not yet ruled on, see Open decisions tab. | Thief and Spy have no effect on Untouchable | To do
L4-04 | 4 · Kits | Scientific | alwaysUpgraded trait on Spy, permanent and free. | Rules spec §4 | L4-03 | M | High | Mandatory test: a Spy card bought mid-game arrives already upgraded, and every held copy is too. | Purchase on turn 12: card upgraded without consuming an upgrade point | To do
L4-05 | 4 · Kits | Assassin and multiple attacks | Several attack cards count as a single action. Each attack targets freely and keeps its own independent resolution. | Rules spec §4 · Spec §5.2 | L4-04 | L | Medium | Stays within the 30s turn: this is not a sub-choice. Each attack creates its own pendingEffect. | 3 attacks played in one turn, independent resolutions | To do
L5-01 | 5 · Special cards | Special card model | Single use, not purchasable individually, upgrade lost on use, joins the pool after use. | Rules spec §5 | L4-02 | M | Low | — | A used card permanently disappears from the hand | To do
L5-02 | 5 · Special cards | Internal counters | Points Generator 3, Imposition 2. Decrements by 1 each time the user loses a life to damage. At 0, the card deactivates and is lost. | Rules spec §5 | L5-01, L0-04 | M | High | The counter does not protect the user. Only applyDamage decrements it, never applyLifeLoss. | A tax does not decrement the counter, an attack does | To do
L5-03 | 5 · Special cards | Suicide | Base: the user is eliminated on their next turn, all opponents lose 5 lives and all their points, no reward for anyone. Upgraded: the user survives and becomes the eliminator. | Rules spec §5 | L5-01 | L | High | Life loss outside of attack. Each opponent plays one turn before the user's next turn: every effect resolves before their elimination. | Partial case tested: 2 of 3 opponents eliminated, the user dies afterward | To do
L5-04 | 5 · Special cards | Spy Thief | Steals all points from all opponents with no cap and spies on all of them. Upgraded: points doubled and all resources visible. | Rules spec §5 | L3-05, L4-03 | M | Medium | Interaction with Untouchable's immunity not yet ruled on — Untouchable holds this very card. | Theft and spying applied to all opponents simultaneously | To do
L5-05 | 5 · Special cards | Imposition | Each opponent cedes 2 points per turn, or 1 life if they don't have enough, which the user gains. Upgraded: 4 points or 2 lives. | Rules spec §5 | L5-02 | M | Medium | Periodic effect triggered on the target's turn, after their action. The life gain is subject to the 25-life cap. | Target with 1 point: they cede 1 life, the user gains it | To do
L5-06 | 5 · Special cards | Cloning | Full state replacement with an opponent's. Cancels pending effects against the user, inherits none from the target, resets visibility to zero both ways. | Rules spec §5 | L3-05, L4-01 | L | High | The clone inherits the kit, therefore its traits. Upgraded version: +10 points, +2 upgrade points, +4 lives, 25-cap applied. | Visibility wiped both ways, incoming effects queue cleared | To do
L5-07 | 5 · Special cards | Sentence | Eliminates a randomly drawn player among everyone in the game, user included. Upgraded: the user is excluded from the draw. | Rules spec §5 | L0-05, L5-01 | M | Medium | Self-elimination: no reward for anyone, cards to the pool. | Reproducible draw with a fixed seed, self-targeting possible in the base version | To do
L5-08 | 5 · Special cards | Points Generator | 2 points per turn, 4 in the upgraded version, as long as the internal counter isn't depleted. | Rules spec §5 | L5-02 | S | Low | — | Gain on the user's turn, stops at zero counter | To do
L5-09 | 5 · Special cards | Special card purchase | 20 points, random draw restricted to the 6 special cards in the V1 lot. | Rules spec §5 · Spec §6.2 | L5-01, L0-05 | S | Low | V1 scope restriction, not a game rule. Do not draw from the full 20-card list. | Only the 6 cards in the lot can come out of the draw | To do
L6-01 | 6 · Elimination | Elimination rewards | The eliminator picks 2 rewards among: 4 lives, 8 points, a card from the eliminated player, an upgrade point. Both choices can be identical. | Rules spec §6 | L1-13 | M | Medium | The life gain is subject to the 25-life cap. | Both choices applied correctly, card transferred if chosen | To do
L6-02 | 6 · Elimination | Multiple elimination | 2 rewards per eliminated player, cumulative, choices chainable. | Rules spec §6 · Spec §6.2 | L6-01 | M | Medium | Upgraded Suicide can trigger several at once: up to 6 choices in a row at 4 players. | Full choice sequence playable without getting stuck | To do
L6-03 | 6 · Elimination | Reward sub-choice | 20s timer per choice. On expiry: 2 × 4 lives granted by default. | Spec §5.5 · §5.6 | L6-02 | M | Low | Never silently waste an already-paid card. | On expiry, lives are granted with no intervention | To do
L6-04 | 6 · Elimination | Elimination without an eliminator | Tax's life cost, self-targeted Sentence, non-upgraded Suicide, elimination by absence: no reward, cards to the pool. | Rules spec §6 | L6-01, L2-06 | S | Low | — | No player receives a reward, the pool receives the cards | To do
L6-05 | 6 · Elimination | Simultaneous eliminators | Reward goes to the eliminator with the fewest remaining lives, then fewest points, then a random draw among ties. | Rules spec §6 | L6-01, L0-05 | M | Medium | Italicized clause in the spec: status to confirm (validated rule or hypothesis). See Open decisions tab. | Correct tie-break in all three scenarios | To do
L7-01 | 7 · Robustness | Reconnection window | 60 seconds triggered the instant of disconnection, in real time, independent of the current turn. Reconnection before expiry: no effect. | Spec §5.7 | L1-13 | M | Medium | The counter starts at disconnection, not at the player's turn. | 40s disconnection then reconnection: no consequence | To do
L7-02 | 7 · Robustness | Absent player | Beyond 60s: immediate draw on each of their turns, without waiting the 30s. Elimination after 3 automatic turns, no reward. Remains a valid target. | Spec §5.7 | L7-01, L6-04 | M | Medium | Any reconnection resets both the 60-second window and the 3-turn counter. | Elimination on the 3rd automatic turn, cards to the pool | To do
L7-03 | 7 · Robustness | Connected inactivity | The 30-second timer expires, the player draws. Elimination after 5 consecutive expired turns. | Spec §5.7 | L7-02 | S | Low | Independent mechanism from disconnection, threshold deliberately higher. | Elimination on the 5th consecutive expired turn | To do
L7-04 | 7 · Robustness | Win by forfeit | At 2 players, elimination by absence or inactivity gives the win to the remaining player. | Spec §5.7 | L7-03 | S | Low | — | Game end correctly declared | To do
L7-05 | 7 · Robustness | 3 and 4-player games | Full playthroughs with the 4 kits, special cards, disconnections, and sub-choices. | Spec §1 | L7-04, L5-09 | L | High | Central goal of V1: a 4-player game plays start to finish without getting stuck. | Three 4-player games completed with no stuck state or inconsistency | To do
L8-01 | 8 · Game log | Log schema | Table of finished games: kits distributed, winner, turn count, cards played per player, eliminations and their cause, final resources. | Spec §3 | L7-05 | M | High | Define this BEFORE the first playtests. A game not logged is lost forever for balancing. | The schema covers the metrics needed for the future balancing work | To do
L8-02 | 8 · Game log | End-of-game write | One single Postgres write, at the end of each game. Never the state of an in-progress game. | Spec §3 | L8-01 | S | Medium | A write failure must never interrupt or invalidate the game. | The game writes once, in-progress state is never persisted | To do
L9-01 | 9 · Polish | Visible degraded states | Absent player, automatic-turn counter before elimination, turn and sub-choice timers. | Spec §7 | L7-03 | M | Low | — | States are readable without opening the console | To do
L9-02 | 9 · Polish | Browsable action log | Complete history since the start of the game, including card identity, purchases and upgrades included. | Spec §7 | L1-12 | M | Medium | Every action is public: the log is the players' primary source of information. | A player can browse the entire game's history | To do
L9-03 | 9 · Polish | End screen | Winner and game recap, return to home. | Spec §7 | L1-13 | S | Low | — | Screen displayed at game end, return to home works | To do

## Milestones
Milestone | Reached at the end of | What must be true | Expected proof | Task count
M1 | Lot 1 · Vertical slice | Two players play a complete game with a single attack card. | Delayed resolution works, hidden information is verified by an automated test, the timer triggers a draw, a winner is declared. | 13
M2 | Lot 3 · Action cards | The full economy and the 10 shared cards work. | 20 card tests green, visibility matrix isolated in its own module, turn ledger reliably distinguishes spending from theft. | 9
M3 | Lot 5 · Special cards | The 4 kits and 6 special cards are playable. | 32 card tests green, kit traits verified on late acquisition, internal counters correct. | 9
M4 | Lot 7 · Robustness | A 4-player game plays start to finish, disconnections and inactivity handled. | Three 4-player games completed with no stuck state. This is the milestone that authorizes playtesting with friends. | 5
M5 | Lots 8 and 9 | The game log records data, the interface is readable. | A finished game produces one usable row in the database. Ready for balancing-data collection. | 3
Task count = number of tasks in the lot named in column B only, not the cumulative count since the start.

## Open decisions
# | Topic | What is not decided | Blocks | Recommendation | Status
1 | Rules spec §6 and §2 not yet corrected | The clause "the weaker attack is automatically cancelled; the stronger one continues" is still present at line 243, and the §2 note reinforces it at line 55. Both contradict the ruling this session locked in — in English just as much as in French. | L2-05 · the entire attack logic | Rewrite both paragraphs before starting lot 2. Two paragraphs, not a session — exact replacement wording provided alongside this backlog. | Open
2 | Effect model | A registry of typed handlers, one per card, versus a generic effect engine driven by data. | L0-03 · the entire card structure | Typed handler registry. Local readability, per-card testability, and the agent can't break Cloning while touching Absorber. | Open
3 | Tooling | Package manager, test runner, client build tool, Node version. The spec requires "clean tsc, clean linter, green tests" without naming any tool. | L0-01 | Choose explicitly, or knowingly delegate to the agent and accept that you're delegating. | Open
4 | Game log schema | Which metrics to record for the future balancing work. | L8-01 · and any serious playtest | Define before the first game is played with friends. An unlogged game can never be recovered. | Open
5 | Simultaneous eliminators | The tie-break clause is italicized in the rules spec §6. In this document, italics seem to mark unvalidated hypotheses (as with the Duplicator). | L6-05 | Confirm its status: validated rule or an untested hypothesis. If a hypothesis, pull it out of V1 scope. | Open
6 | Untouchable's immunity against Spy Thief | Its ability names "Thief and Spy". Spy Thief produces both effects under a different name. The case is reachable in V1: Untouchable holds this very card, and any other player can obtain it by purchase or elimination reward. | L5-04 | Rule on this before lot 5. Literal reading: no immunity. Functional reading: immunity applies. | Open
7 | Timers absent from the rules spec | Turn timer, reconnection window, and elimination thresholds exist only in this technical spec. | None — non-blocking | Confirm this is a deliberate choice (video-game rules kept out of the rules spec) rather than an oversight of the update. | Open

## Legend
How to read this backlog
Sequencing principle | The thinnest possible vertical slice first: a 2-player game playable with a single attack card (lot 1), then content stacks on top of it. Do not build all 16 cards before a single game runs end to end — integration problems are cheapest to catch early and most expensive to discover last.
Execution order | Follow the ID order. The "Depends on" column gives the strict prerequisites. Two tasks with no shared dependency can be run in parallel, but a solo developer gains little from that.
Complexity | S: one agent pass, quick review. M: several passes, careful review. L: to be broken into sub-tasks by the agent before any code is written.
No time estimates in hours: with an agent, writing the code is no longer the bottleneck. Review and correction time is — and that depends on how clear the spec is, not on how much code gets written.
Risk | High: an error here triggers no alert and surfaces weeks later. Read the produced code line by line, don't settle for green tests.
Medium: error detectable while playing, but costly to fix after the fact.
Low: error visible immediately.
Three tasks to never defer | L0-04 (the two life-loss primitives), L1-07 (the delayed resolution queue), and L1-09 (the per-recipient view). Each is a foundation: added after the fact, it forces a rework of everything built on top of it.
References | Rules spec §N refers to spec_bataille_des_cartes_en.md. Spec §N refers to technical_spec_v1.md. No rule is copied here: when in doubt, read the source.
Out of scope | The 11 remaining kits, Team / God / Quick modes, bots, user accounts, persistence of an in-progress game, monetization, art direction. See technical spec §9.